## Slide 1: Group 4 Tạ Đức Duy Trần Khánh Duy, Vũ Duy Hào, Nguyễn Lê Hoàng, Bùi Trần Hoàng, Đỗ Nhật Hoàng, Nguyễn Gia Huy, Phạm Xuân Hùng, Nguyễn Duy Đức

## Slide 2: Contents
How to Select the Best Project?
How to Determine Project Duration?
How to Allocate Resources Effectively?
How to Reduce Project Duration?

## Slide 3: How to Select the Best Project?

## Slide 4: Weighted Scoring Model
Provide a process for selecting projects based on many criteria:
  Identify important criteria for project selection
  Assign weights (%) to each criterion so that they add up to 100%
  Assign scores to each criterion for each project
  Multiply the scores by the weights and get the total weighted scores
The higher the weighted score, the better

## Slide 5: Weighted Scoring Model (cont)
 Project 3 is the best one
Score
Weight
Criteria
Project 6
Project 5
Project 4
Project 3
Project 2
Project 1
6
9
8
10
7
10
25%
ROI
8
9
8
8
9
6
10%
Stay with core competencies
9
6
9
7
6
8
30%
Defect reduction
8
8
6
9
8
7
20%
Sale improvement
6
8
7
9
8
9
10%
Customer loyalty improvement
6
9
6
8
7
8
5%
Environmental friendly
7.5
7.8
7.7
8.5
7.2
8.2
100%
Weighted Scores

## Slide 6: How to Determine Project Duration?

## Slide 7: Process for Determining Project Duration
Draw AOA diagram
Identify the critical path and critical activities (activities lie on the critical path)
Project duration = total duration of critical activities

## Slide 8: Drawing AOA Diagram
Project 3 |  | 
Activity | Predecessor | Time (week)
A | None | 2
B | None | 3
C | B | 5
D | B | 6
E | A, C | 8
F | A, C | 4
G | A, C | 3
H | D, G | 2
I | E | 1
1
3
2
A(2)
B(3)
5
D(6)
C(5)
4
E(8)
G(3)
6
F(4)
H(2)
I(1)

## Slide 9: Finding Critical Path
Tip for finding a critical path:
  Calculate the Earliest Starting Time (EST) of each event by using forward scanning
  Calculate the Latest Finishing Time (LFT) of each event by using backward scanning
  Critical path passes through events whose EST and LFT are equal
Notice: event is represented by a red circle in the diagram.

## Slide 10: Finding Critical Path (cont)
Calculate the Earliest Starting Time (EST)
1
3
2
A(2)
B(3)
5
D(6)
C(5)
4
E(8)
G(3)
6
F(4)
H(2)
I(1)
EST
LFT
2
8
11
9
13
12
17
Forward Scanning
0
8
16
3
11
17

## Slide 11: Finding Critical Path (cont)
Calculate the Latest Finishing Time (LFT)
1
3
2
A(2)
B(3)
5
D(6)
C(5)
4
E(8)
G(3)
6
F(4)
H(2)
I(1)
3
9
12
13
8
Backward Scanning
EST
LFT
0
0
8
8
16
16
17
17
11
15
3
3
0
6

## Slide 12: Finding Critical Path (cont)
1
3
2
A(2)
B(3)
5
D(6)
C(5)
4
E(8)
G(3)
6
F(4)
H(2)
I(1)
EST
LFT
0
0
8
8
16
16
17
17
11
15
3
3
è
Critical path: 1
–
2
–
3
–
4
–
6
è
Critical activities: B
–
C
–
E
–
I
è
Project
duration
=
3
+
5
+
8
+
1
=
17
week
s

## Slide 13: How to Allocate Resources Effectively?
 Using Gantt Chart

## Slide 14: Example
Project 3 |  |  | 
Activity | Predecessor | Time (week) | Workforce (person/week)
A | None | 2 | 6
B | None | 3 | 8
C | B | 5 | 10
D | B | 6 | 18
E | A, C | 8 | 25
F | A, C | 4 | 45
G | A, C | 3 | 60
H | D, G | 2 | 15
I | E | 1 | 12
 Requirement: Allocate workforce so that do not use more than 85 people per week.

## Slide 15: Example (cont) Why > 85 people/week?
Activity | Predecessor | Time (week) | Labor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A | none | 2 | 6 | 6 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | none | 3 | 8 | 8 | 8 | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | B | 5 | 10 |  |  |  | 10 | 10 | 10 | 10 | 10 |  |  |  |  |  |  |  |  | 
D | B | 6 | 18 |  |  |  | 18 | 18 | 18 | 18 | 18 | 18 |  |  |  |  |  |  |  | 
E | A, C | 8 | 25 |  |  |  |  |  |  |  |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 
F | A, C | 4 | 45 |  |  |  |  |  |  |  |  | 45 | 45 | 45 | 45 |  |  |  |  | 
G | A, C | 3 | 60 |  |  |  |  |  |  |  |  | 60 | 60 | 60 |  |  |  |  |  | 
H | D, G | 2 | 15 |  |  |  |  |  |  |  |  |  |  |  | 15 | 15 |  |  |  | 
I | E | 1 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12
Weeks |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Total labors/week |  |  |  | 14 | 14 | 8 | 28 | 28 | 28 | 28 | 28 | 148 | 130 | 130 | 85 | 40 | 25 | 25 | 25 | 12
 Invalid workforce distribution (since weeks 9 – 11 use more than 85 people)

## Slide 16: Example (cont) Balancing Workforce Distribution
Activity | Predecessor | Time (week) | Labor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A | none | 2 | 6 | 6 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | none | 3 | 8 | 8 | 8 | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | B | 5 | 10 |  |  |  | 10 | 10 | 10 | 10 | 10 |  |  |  |  |  |  |  |  | 
D | B | 6 | 18 |  |  |  | 18 | 18 | 18 | 18 | 18 | 18 |  |  |  |  |  |  |  | 
E | A, C | 8 | 25 |  |  |  |  |  |  |  |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 
F | A, C | 4 | 45 |  |  |  |  |  |  |  |  |  |  | 45 | 45 | 45 | 45 |  |  | 
G | A, C | 3 | 60 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 60 | 60 | 60
H | D, G | 2 | 15 |  |  |  |  |  |  |  |  |  |  |  | 15 | 15 |  |  |  | 
I | E | 1 | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12
Weeks |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Total labors/week |  |  |  | 14 | 14 | 8 | 28 | 28 | 28 | 28 | 28 | 43 | 25 | 70 | 85 | 85 | 70 | 85 | 85 | 72
Delay Time
Delay Time
 Solution: Delay non-critical activities.

## Slide 17: How to Reduce Project Duration?

## Slide 18: Solution for Reducing Project Duration
Shortening the duration of critical activities:
  Add more resources (e.g. workers, machines)
  Reallocate the available resources
    Shifting resources from non-critical activities to critical activities

## Slide 19: Summary
How to Select the Best Project?
   Using the weighted scoring model
How to Determine Project Duration?
   Using the AOA diagram, critical path & critical activities
How to Allocate Resources Effectively?
   Using the Gantt chart, delaying non-critical activities
How to Reduce Project Duration?
   Adding resources, reallocating the available resource