## Slide 1: Lecture 5 Developing a project plan
Contents
            What is a Project network?
            Why is project network needed?
            How to develop a project network?
            How to compute a project time?
            How to make the network close to reality?

## Slide 2: What is a project network?
  Project network is a flow chart that graphically depicts the sequence, interdependencies, and start and finish times of the project activities
  Project activities are the individual actions that must be completed to achieve project success

## Slide 3: What is a project network
Activity - On - Node

## Slide 4: What is a project network
Activity - On - Arrow
A
B
D
E
F
G
H
K
C
L
I

## Slide 5: Why is project network needed?
Develop a project time plan which includes:
- Sequence of activities
- Start and finish time
- Project duration
Develop other project resource plans including:
- Human resource
- Physical resource
- Financial resource
- Outsourcing

## Slide 6: How to develop a project network?
          Terminology
          Basic rules for constructing a project network
          Two Approaches in constructing a project network

## Slide 7: Terminology
Activity: an element of the project that requires time
Activity – on – Node: Uses a node to depict an activity
- ES: Early start
- EF: Early finish
- LS: Late start
- LF: Late finish
- SL: Slack time = LS – ES or LF - EF
ES
EF
LS
LF
Label
Activity name
Duration
SL

## Slide 8: Terminology
Activity – on – Arrow: Uses an arrow to depict an activity
Name or Label
(Duration, resources)
Start
Finish
Direction from left to right

## Slide 9: Terminology
Merge activity: an activity that has two or more preceding activities on which it
depends
Parallel (concurrent) activities: Activities that can occur independently and, if
desired, not at the same time.

## Slide 10: Terminology
Path: a sequence of connected, dependent activities
Critical path: the longest path through the activity network that allows for the completion of all project-related activities. The shortest expected time in which the entire project can be completed. Delays on the critical path will delay completion of the entire project.
A
B
D
G
F
H
I
C
K
E
A – B – E – K
A – B – F – I – K
A – C – I – K
A – D – G – H - K

## Slide 11: Terminology
Event: a point in time when an activity is started or completed.
Dummy activity: The activity that does not consume time.
Burst activity: an activity that has more than one activity immediately following
it (more than one dependency arrow flowing from it).
B
D
A
C

## Slide 12: Basic rules for constructing a project network
Networks typically flow from left to right
An activity cannot begin until all of its preceding activities are complete
Arrows indicate precedence and flow and can cross over each other
Identify each activity with a unique number; this number must be greater than its predecessors
Looping is not allowed

## Slide 13: Two Approaches in constructing a project network
Activity – On – Node (AON): Uses a node to depict an activity
Activity – On – Arrow (AOA): Uses an arrow to depict an activity

## Slide 14: Activity – on – node (AON)
Fundamentals for developing a project network by AON

## Slide 15: Activity – on – node (AON)
Fundamentals for developing a project network by AON

## Slide 16: Activity – on – node (AON)
Network information

## Slide 17: Activity – on – node (AON)

## Slide 18: Activity – on – arrow (AOA)
Fundamentals for developing a project network by AOA
Dummy Activity

## Slide 19: Activity – on – Arrow (AOA)
Fundamentals for developing a project network by AOA

## Slide 20: Activity – on – Arrow (AOA)
Fundamentals for developing a project network by AOA

## Slide 21: Activity – on – Arrow (AOA)
Network information

## Slide 22: Activity – on – Arrow (AOA)

## Slide 23: How to Compute a project time?
            Network computation process
            AON case
            AOA case

## Slide 24: Network computation process
              Forward Pass Computation
              Backward Pass Computation
              Determining slack time

## Slide 25: Forward Pass Computation
Start from the left and go to the right of the network
Add activity times along each path in the network (ES + Duration = EF).
Carry the early finish (EF) to the next activity where it becomes its early start (ES) unless the next succeeding activity is a merge activity, in which case the largest EF of all preceding activities is selected.
Where:
    - ES (Early start): How soon can the activity start?
    - EF (Early finish): How soon can the activity finish?
    - ET (Expected time): How soon can the project finish?

## Slide 26: Backward Pass Computation
Start from the right and go back to the left of the network
Subtract activity times along each path in the network (LF - Duration = LS).
Carry the late start (LS) to the next activity where it becomes its late finish (LF) unless the next succeeding activity is a burst activity, in which case the smallest LF of all preceding activities is selected
Where:
        - LS (Late start): How late can the activity start?
        - LF (Late finish): How late can the activity finish?
        SL (Slack time or flow): How long can it be delayed?

## Slide 27: Backward Pass Computation
Free Slack (or Float)
The amount of time an activity can be delayed without delaying connected successor activities
Total Slack
The amount of time an activity can be delayed without delaying the entire project
The critical path is the network path(s) that has (have) the least slack in common.

## Slide 28: Activity – on – node (AON)
Network information

## Slide 29: Activity – on – node (AON)

## Slide 30: Activity – on – node (AON)
Forward pass computation

## Slide 31: Activity – on – node (AON)
Backward pass computation

## Slide 32: Activity – on – node (AON)
Network with slack time

## Slide 33: Activity – on – node (AOA)
Network information

## Slide 34: Activity – on – node (AOA)

## Slide 35: Activity – on – node (AOA)
Forward pass computation

## Slide 36: Activity – on – node (AOA)
Backward pass computation

## Slide 37: Activity – on – node (AOA)
Network with slack time

## Slide 38: Comparison of AON and AOA Methods

## Slide 39: How to make the network close to reality?
Laddering technique
  Activities are broken into segments so the following activity can begin sooner and not delay the work.
Lagging technique
  The minimum amount of time a dependent activity must be delayed to begin or end
  Lengthy activities are broken down to reduce the delay in the start of
  successor activities.
  Lags can be used to constrain finish-to-start, start-to-start, finish-to-finish,
  start-to-finish, or combination relationships.

## Slide 40: Laddering technique

## Slide 41: Lagging technique

## Slide 42: Lagging technique

## Slide 43: Key Terms
Activity
Activity-on-arrow (AOA)
Activity-on-node (AON)
Burst activity
Concurrent engineering
Critical path
Early and late times
Gantt chart
Hammock activity
Lag relationship
Merge activity
Network sensitivity
Parallel activity
Slack/float—total and free

## Slide 44: You are required to develop a project network and compute the project time using two approaches: AON and AOA
Activity | Preceding activity | Activity time (Week) | Workforce (Persons/week) | Machine (Unit/week)
A | None | 2 | 5 | 2
B | None | 1 | 6 | 2
C | None | 3 | 3 | 5
D | A | 2 | 4 | 6
E | B, D | 4 | 5 | 4
F | B, D | 5 | 8 | 3
G | C, E | 6 | 6 | 1

## Slide 45: You are required to develop a project network and compute the project time using two approaches: AON and AOA
0 | A | 2 |  | 2 | D | 4 |  |  | 4 | F | 9 |  |  |  | 
0 |  |  |  | 0 |  |  |  |  | 5 |  |  |  |  |  | 
0 | 2 | 2 |  | 2 | 2 | 4 |  |  | 9 | 5 | 14 |  |  |  | 
0 | B | 1 |  |  |  |  |  |  | 4 | E | 8 |  |  |  | 
3 |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  | 
3 | 1 | 4 |  |  |  |  |  |  | 4 | 4 | 8 |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | 8 | G | 14
0 | C | 3 |  |  |  |  |  |  |  |  |  |  | 0 |  | 
5 |  |  |  |  |  |  |  |  |  |  |  |  | 8 | 6 | 14
5 | 3 | 8 |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 46: You are required to develop a project network and compute the project time using two approaches: AON and AOA
A(2)
B(1)
C(3)
D(2)
E(4)
F(5)
G(6)
0
0
2
2
2
2
4
4
0
3
1
4
0
5
3
8
4
4
8
8
4
9
9
14
8
8
14
14